## Quotation
Project description |  | Curzon Street |  |  | Revision | 0 |  |  | 350 | Supervisor - £350
[5 empty] | Date | 2019-07-03 19:16 |  |  | 260 | Brickie - £260
[9 empty] | 130 | Labour - £130
BoQ | Supplier | Description | Quant | unit | Rate | Add/omit |  | LABOUR |  |  |  | MATERIALS | [5 empty] | WASTAGE | PLANT | TOTAL INC PROFIT
A |  | B | C | D | E | F |  | 1 no Gangs of 2 brickie & 1 labour
[8 empty] | 650 | day | [10 empty] | 14775.3725 | inc 15%
|  | MASONRY | [8 empty] | 1 |  | 75 | 25kg bags | 4.05 | 303.75 |  | 318.9375
|  | F10: BRICK/BLOCK WALLING - all materials provided by others | [5 empty] | 62.35
[11 empty] | 2 |  | 235 | 25kg bags | 2.55 | 599.25 |  | 629.2125 | 1500
|  | brickwork wall, single brick thick, labour only install | 260 | m2 | 62.1 | 16146 | 1 Gang Say 25m2 day | 3250 | 5 days |  | 3 |  |  | no | 50 per pack | 0 |  | 0
[6 empty] | 0 | [6 empty] | 2600 | no | 2.5 | 6500 |  | 7150
|  | Extra, forming vertical movement joints | 42 | m | 28.5 | 1197 | 1 gang 1 day | 650 | 1 day | 18.69 | [7 empty] | 8098.15
0
|  | Extra, forming cavity trays excluding weep holes | 52 | m | 5.88 | 305.76
0
|  | Extra, copings to top of walls | 52 | m | 13.11 | 681.72 |  | 65 | 0.5 days |  | 3 |  | 750.7378 | 0.09 | 67.5664 |  |  | 70.9447 |  | 1622.2878 | inc 15%
[6 empty] | 0 |  |  |  |  | 4 |  |  | 3.5 | 0 |  |  | 0 |  | 304.75 | inc 15%
|  | Extra, install shelf angles | 37.98 | m | 17.89 | 679.4622 |  | 250 | 1 day
[11 empty] | 5 |  | 187.6844 | 3.5 | 656.8956 |  |  | 689.7403
|  | Windposts |  |  |  | Excluded | [8 empty] | 125 |  |  | 760.6851
[7 empty] | Gang 4 per d | 2925 | [6 empty] | 75
|  | MASONRY | [8 empty] | 6 |  | 8 | 3.5 | 28 |  |  | 29.4 |  | 499.6577 | inc 15%
|  | STONE CLADDING LOUVRE - all materials provided by others | [8 empty] | 7 |  | 42.2 | 3.5 | 147.7 |  |  | 155.085
|  | Install only of stainless steel posts | 1 | item | 8214 | 8214
0
|  | Extra, Paint black | 1 | item | 720 | 720
0
|  | Extra, install netting mesh | 73 | m2 | 3.88 | 283.24
0
|  | Fix stone metal plates to posts | 73 | m2 | 65.55 | 4785.15 | [11 empty] | 184.485
0
|  | Extra, copings to top of walls | 26 | m | 29.1 | 756.6
[6 empty] | 0 | [13 empty] | 18084.0236 | inc 15%
|  | Prelims including supervision, QS, H&S, tools, storage, PPE | 4 | weeks | 3490 | 13960
[6 empty] | 0 |  | 3 MEN | 1 GANG TO BE USED | [5 empty] | 72 | 5 | 360 | 378
[6 empty] | 0 |  | 7 | TOTAL DAYS
[8 empty] | PRELIMS | [6 empty] | 18 | 8 | 144 | 151.2
[8 empty] | Task lights | exc
[8 empty] | Genie for WPs | 400 | [5 empty] | 18 | 15 | 270 | 283.5
[6 empty] | 47728.9322 |  | Buckets | 8
Clarifications | [5 empty] | 0 |  | Trowels | 12 | [5 empty] | 18 | 38 | 684 | 718.2
|  | This price is based on drawings provided only - no specification for our works has been provided. No blockwork has been allowed |  |  |  | 0 |  | Drills | 25
|  | We require Careys to provide scaffold access for us to install the works | [5 empty] | Brick saw | 95 | [5 empty] | 25 | 4 | 100 | 105
|  | We require Careys to set out walls from gridlines. We have not allowed for an engineer. | [5 empty] | Mixer | 75
|  | All materials to be provided free of charge. We have only allowed for labour only | [5 empty] | Cleaning product | 0 | [5 empty] | 18 | 13 | 234 | 245.7
|  | We have not allowed any delay costs within our price for weather which will inhibit the progress of our works | [5 empty] | Tool chest | 0
|  | Safety and task lighting to be provided by others. | [5 empty] | Van | 100 |  |  |  | 86.818 |  | 86.818 | 111 | 9636.798 | 10118.6379
|  | We require an area close to the works to store materials/tools. |  |  |  | 0 |  | Fuel | 350
|  | We require 110v power connection close to the works, provided by others. |  |  |  | 0 |  | Parking | 155 | [5 empty] | 1 |  |  | 800
|  | We require a water point within 15m of our workface, provided by others. | [5 empty] | Barriers | 15
|  | We require clear unhindered access to complete these works. We have allowed for 1 continuous visit only. | [5 empty] | Supervisor | 1750 | 350 | 5 | DAYS | [5 empty] | 12800.2379
|  | We have not allowed to remove waste from our workface or site for these works. Skips to be provided by others in location of workface. | [5 empty] | QS | 250
|  | We have not allowed any fire stopping works or insulation | [5 empty] | H&S | 150
|  | All offloading, horizontal/vertical movement of materials to workface excluded. We have not allowed for a forklift or driver. | [5 empty] | PPE | 15
Please note this is a lump sum offer and is not subject to remeasure
We have made no allowance for lighting works.
We have not allowed to install any sheeting such as dpc or roof waterproofing membranes
|  | We have not allowed any works to the planters | [5 empty] | Tools | 50
|  | Total excludes VAT | [5 empty] | Facemasks | 25
|  | We have not allowed to take any design responsibility | [5 empty] | protection | 15
Programme Implications | [5 empty] | 0 |  |  | 3490
0
|  | Sub Total measured works |  |  |  | 47728.9322
|  | Total Value £ |  |  |  | 47728.9322

## SoRs
Project description |  | Schedule of Daywork Rates |  |  | Revision | 1
[5 empty] | Date | 2019-07-03 19:16
BoQ | Supplier | Description | Quant | unit | Rate | Add/omit
A |  | B | C | D | E | F
0
Daywork Rates
0
|  | Supervisor - £350 |  |  |  | 0
Quantity Surveyor - £320
|  | Tiler - £250 |  |  |  | 0
|  | Carpenter - £270 |  |  |  | 0
|  | Labourer - £130 |  |  |  | 0
Brickworker - £260
Non Productive working:
|  | Saturday 8am to 5pm 150% |  |  |  | 0
Sunday 8am to 4pm 200%
Note: Labour rates exclude Supervision
|  | Plant + 15% |  |  |  | 0
|  | Subcontractors cost + 15% |  |  |  | 0
Materials cost + 15%
0
0
Clarifications | [5 empty] | 0
0
Programme Implications | [5 empty] | 0
0
|  | Sub Total measured works |  |  |  | 0
|  | Total Value £ |  |  |  | 0

## Dims
measure
| Section 1 Wall | [5 empty] | Section 2 Wall |  |  |  |  | WINDPOSTS
|  | ave m |  | left | right |  |  | ave m | Total | left | right | M | NO
section 1 | length | 3.542 |  |  |  | section 1 | length | 2.361 | 7.083 |  |  | 2.19 | 1 | 2.19
| height | 2.795 |  | 2.19 | 3.4 | 3 parts | height | 4.832 | 4.832 | 4.832 | 4.832 | 3.4 | 2 | 6.8
| sidecuts | 5.59 |  |  |  | the same | sidecuts | 9.664 | 28.992 |  |  | 4.67 | 2 | 9.34
| head | 4.5 |  |  |  |  | head | 2.361 | 7.083 |  |  | 5.6 | 3 | 16.8
| ties @ 450mm | 12.4222 |  |  |  |  | ties @ 450mm | 21.4756 | 64.4267 |  |  | 4.832 | 6 | 28.992
| m2 block 215mm | 9.8999 |  |  |  |  | m2 block 215mm | 11.4084 | 34.2251 |  |  | 5.664 | 2 | 11.328
[12 empty] | 5.684 | 2 | 11.368
|  | ave m |  | left | right |  |  | ave m |  | left | right |  |  | 86.818 | m
section 2 | length | 3.4 |  |  |  | section 2 | length | 6.819
| height | 4.035 |  | 3.4 | 4.67 | 2 parts | height | 2.832 |  | 5.664 | 5.664
| sidecuts | 8.07 |  |  |  |  | sidecuts | 11.328
| head | 4.5 |  |  |  |  | head | 6.819
| ties @ 450mm | 17.9333 |  |  |  |  | ties @ 450mm | 25.1733
| m2 block 215mm | 13.719 |  |  |  |  | m2 block 215mm | 19.3114
|  | ave m |  | left | right |  |  | ave m |  | left | right
section 3 | length | 3.4 |  |  |  | section 3 | length | 10.3
| height | 5.135 |  | 4.67 | 5.6 | 4 parts | height | 2.842 |  | 11.368 | 11.368
| sidecuts | 10.27 |  |  |  |  | sidecuts | 22.736
| head | 4.5 |  |  |  |  | head | 10.3
| ties @ 450mm | 22.8222 |  |  |  |  | ties @ 450mm | 50.5244
| m2 block 215mm | 17.459 |  |  |  |  | m2 block 215mm | 29.2726
|  | ave m |  | left | right
section 4 | length | 2.9 |  |  |  |  | sidecuts | 84.458 | lm
| height | 5.6 |  | 5.6 | 5.6 |  | head | 37.98 | lm
| sidecuts | 16.8 |  |  |  |  | ties @ 450mm | 187.6844 | no
| head | 5 |  |  |  |  | m2 block 215mm | 140.127 | m2
| ties @ 450mm | 37.3333 |  |  |  |  | lintol | 1
| m2 block 215mm | 16.24
| lintol | 1.3 | m